## Sheet1
id | Activity Name | duration | predecessors | O | M | P
1 | Project Initiation | 5 |  | 3 | 5 | 7
2 | Requirement Gathering | 10 | 1 | 8 | 10 | 12
3 | Feasibility Study | 7 | 1 | 5 | 7 | 9
4 | Design System Architecture | 14 | 2 | 12 | 14 | 16
5 | Develop Module A | 20 | 4 | 18 | 20 | 22
6 | Develop Module B | 15 | 4 | 13 | 15 | 17
7 | Develop Module C | 10 | 4 | 8 | 10 | 12
8 | Integration Testing | 12 | 5,6,7 | 10 | 12 | 14
9 | User Acceptance Testing | 8 | 8 | 6 | 8 | 10
10 | Documentation | 5 | 2,9 | 4 | 5 | 6
11 | Procure Hardware | 15 | 3 | 12 | 15 | 18
12 | Setup Development Environment | 7 | 11 | 5 | 7 | 9
13 | Database Design | 10 | 2 | 8 | 10 | 12
14 | Backend Development | 18 | 13 | 15 | 18 | 21
15 | Frontend Development | 15 | 13 | 12 | 15 | 18
16 | API Integration | 10 | 14,15 | 8 | 10 | 12
17 | Performance Testing | 5 | 16 | 4 | 5 | 6
18 | Security Audit | 7 | 17 | 5 | 7 | 9
19 | Deployment | 10 | 9,18 | 8 | 10 | 12
20 | Post-Implementation Review | 5 | 19 | 4 | 5 | 6