## EVM KPIs
KPI | Value | RAG Status
Earned Value (EV) | $251,988.20 | GREY
Planned Value (PV) | $265,452.60 | GREY
Actual Cost (AC) | $292,999.11 | GREY
Budget at Completion (BAC) | $13,201,000.00 | GREY
Cost Variance (CV) | $-41,010.91 | AMBER
Schedule Variance (SV) | $-13,464.40 | AMBER
Cost Performance Index (CPI) | 0.860 | RED
Schedule Perf. Index (SPI) | 0.949 | RED
Percent Complete (PC) | 1.9% | GREY
Percent Spent (PS) | 2.2% | GREY
Critical Ratio (CR) | 0.816 | AMBER
TCPI (BAC) | 1.003 | GREEN
EAC₁ (Atypical) | $13,242,010.91 | AMBER
EAC₂ (Typical) | $15,349,453.87 | RED
EAC₃ (Composite) | $16,153,960.31 | RED
Variance at Completion | $-41,010.91 | AMBER